## Game Dev Plan
Week | Focus Area | Tasks
Week 1 | Planning & Setup | Finalize story, key missions, and mechanics; Set up project structure and version control.
Week 2–3 | Core Mechanics Development | Implement character controls: movement, crouch, attack.
Week 2–3 | Core Mechanics Development | Create enemy AI behavior: patrols, vision cones, alert states.
Week 4–5 | Game Systems | Implement inventory, health, and detection meters.
Week 4–5 | Game Systems | Create save/load systems and refine gameplay loops.
Week 6–7 | Level Design & Assets | Design detailed levels based on historical locations.
Week 6–7 | Level Design & Assets | Add environmental props, textures, and basic lighting.
Week 7–8 | Polish & Audio | Add sound effects, voiceovers, and background music.
Week 8–9 | Polish & Audio | Improve UI/UX elements, optimize performance.
Week 10 | Final Testing & Release | Playtesting, bug fixing, adjust balancing, finalize release.